## Schedule
✔ | Project | Component/ |  | Duration (Days) | Start | Actual Finish | Expected Finish | FINAL DEADLINE
| ICE TRAK |  |  | 105 | 2016-01-28 |  | 2016-05-12 | 2016-05-12
✔ |  | Framework |  | 14 | 2016-02-09 | 2016-04-22 | 2016-02-23
|  | Inventory Mgmt |  | 56 | 2016-02-05 |  | 2016-04-01
✔ |  |  | Requirements | 4 | 2016-02-05 | 2016-02-19 | 2016-02-09
✔ |  |  | Design | 14 | 2016-02-23 | 2016-03-24 | 2016-03-08
✔ |  |  | Code and Unit Test | 7 | 2016-03-08 | 2016-05-11 | 2016-03-15
|  |  | Integration | 3 | 2016-03-15 |  | 2016-03-18
|  |  | Independent Test | 14 | 2016-03-18 |  | 2016-04-01
|  | Order Entry |  | 77 | 2016-02-05 |  | 2016-04-22
✔ |  |  | Requirements | 4 | 2016-02-05 | 2016-02-19 | 2016-02-09
✔ |  |  | Design | 14 | 2016-03-15 | 2016-03-24 | 2016-03-29
✔ |  |  | Code and Unit Test | 7 | 2016-03-29 | 2016-05-11 | 2016-04-05
|  |  | Integration | 3 | 2016-04-05 |  | 2016-04-08
|  |  | Independent Test | 14 | 2016-04-08 |  | 2016-04-22
|  | Shipment Tracking |  | 77 | 2016-02-05 |  | 2016-04-22
✔ |  |  | Requirements | 4 | 2016-02-05 | 2016-02-19 | 2016-02-09
✔ |  |  | Design | 14 | 2016-03-15 | 2016-03-24 | 2016-03-29
|  |  | Code and Unit Test | 7 | 2016-03-29 |  | 2016-04-05
|  |  | Integration | 3 | 2016-04-05 |  | 2016-04-08
|  |  | Independent Test | 14 | 2016-04-08 |  | 2016-04-22
|  | Trouble Ticket Mgmt |  | 98 | 2016-02-05 |  | 2016-05-13
✔ |  |  | Requirements | 4 | 2016-02-05 | 2016-02-19 | 2016-02-09
✔ |  |  | Design | 14 | 2016-04-05 | 2016-03-24 | 2016-04-19
|  |  | Code and Unit Test | 7 | 2016-04-19 |  | 2016-04-26
|  |  | Integration | 3 | 2016-04-26 |  | 2016-04-29
|  |  | Independent Test | 14 | 2016-04-29 |  | 2016-05-13
Turn-Ins
✔ |  | Form Team | Team ICE TRACK |  |  |  | 2016-01-28
✔ |  | Database Approval |  |  |  |  | 2016-02-09
|  | Deliverable |  | Project Notebook included to all delivers
✔ |  |  | #1: Reqt and Proj Plan |  |  |  | 2016-02-18
✔ |  |  | #2: Test Plan |  |  |  | 2016-03-01
✔ |  |  | #3: Data Model |  |  |  | 2016-03-24
✔ |  |  | #3: Project Architecture |  |  |  | 2016-03-24
✔ |  |  | #4: Proj Plan v. Actual |  |  |  | 2016-05-12
✔ |  |  | #4: Proj Lessons |  |  |  | 2016-05-12
✔ |  |  | #4: Test Report |  |  |  | 2016-05-12
✔ |  | Peer Review | #1 |  |  |  | 2016-02-23
✔ |  |  | #2 |  |  |  | 2016-04-14
| Test |  | ICSM | ESWE | Other
✔ |  | Midterm #1 | 0,6,7,14 | 1-3,5-7,10 | www.itteam-direct.com/gwbadat.htm |  | 2016-03-03
✔ |  | Midterm #2 | 8-10 | 3,4,7-9,11 | www.phlonx.com/resources/nf3/ |  | 2016-04-28
| Presentation | Critiques |  |  |  |  | 2016-05-05
Formulas:
Expected Finish = IFERROR(__xludf.DUMMYFUNCTION("TO_DATE( [Duration (Days)]+ TO_PURE_NUMBER([Start]))"),"5/12/2016")
Expected Finish = IFERROR(__xludf.DUMMYFUNCTION("TO_DATE(TO_PURE_NUMBER([Start])+[Duration (Days)])"),"2/23/2016")
Start = [Start, row below]
Start = [Expected Finish, row above]